## Sheet1
Product Backlog
As a | Priority | User Stories | So that | Sprint | Status
User | High | As a user, I will be able to login | User should be able to login with | 1 | Completed
|  | with username and password | their created user username and
|  | Created by myself so that I can | password to use the system
retrive information and use the features.
| Medium | As a user, I will be able to view | User should be able to view the | 1 | completed
|  | the system so that I can be upto | system
date with the system
| High | As a user, I will be able to use | user should be able to use the | 2 | To do
|  | various features provided by the | features
system
| High | As a user, I will be able to Register | user should be able to register | 2 | To do
|  | my vehicle | their vehicle
| High | As a user, I will be able to use | user should be able to use complain | 2 | To do
|  | complain features which includes | features
document lost, vehicle lost,Incident
report
| High | As a user, I will be able to view my | user should be able to view their | 2 | To do
|  | offense data and can pay the offense | offense and can pay the offense fine
fine
Traffic | High | As a Traffic police I will able to login to system as usename and password | Traffic should be able to login in the system | 2 | To do
Provided by admin
| High | As a traffic, I will be able to view the | Traffic should be able to view the | 2 | To do
|  | offense | offense record
| High | As a traffic I will be able to change my password | Traffic will able to update new password
| High | As a traffic, I will be able to record | Traffic should be able to record the | 2 | To do
|  | offense | offense
| High | As a traffic, I will be able to view the | Traffic should be able to view the | 2 | To do
|  | Complain | Complain
Admin | High | As a Admin, I will be able to login in a system | admin can uses the system | 1 | Completed
| Low | As a Admin, I will be able to post | Admin should be able to post notices | 2 | To do
notices
| Medium | As a Admin, I will be able to add | Admin should be able to traffic police users | 2 | To do
traffic police in a system
| Medium | As a Admin, I will be able to selete | Admin should be able to traffic police users | 2 | To do
|  | traffic police in a system | from system
| High | As a Admin, I wiil be able to view information in system | Admin should be able to manage the data | 2 | To do